## Sheet2
Performance
User Interface/User Experience
Model Issue
Integration
Functional
User Interface/Validation
Data Quality

## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Engineer | 2025-12-11 | API crashes when empty request body is sent. | Sprint 2 | Backend Developer | Functional | Added Pydantic validation for missing fields. | 13-11-2025 | Closed | Working fine after fix
2 | QA Engineer | 2025-12-11 | Age field accepts negative values in UI. | Sprint 3 | Frontend Developer | User Interface/Validation | Added input validation and min-value constraint. | 14-11-2025 | Closed | Issue resolved
3 | Data Scientist | 2025-10-11 | Missing values not handled for Income column in dataset. | Sprint 1 | Data Scientist | Data Quality | Added imputation strategy (median replacement). | 2025-11-11 | Closed | Dataset cleaned
4 | QA Engineer | 13/11/2025 | Confidence score missing in API response . | Sprint 2 | ML Engineer | Functional | Updated model output schema to include confidence. | 13-11-2025 | Closed | Tested & Verified
5 | QA Engineer | 14/11/2025 | CORS error when UI calls backend prediction API. | Sprint 3 | Full Stack Developer | Integration | Enabled CORS middleware in FastAPI. | 14-11-2025 | Closed | Awaiting Deployment
6 | QA Engineer | 14/11/2025 | UI not showing error message for invalid input. | Sprint 3 | Frontend Developer | User Interface/User Experience | Implemented toast notification for validation failures. | 14-11-2025 | Closed | Needs retesting
7 | ML Engineer | 2025-09-11 | Model accuracy below expected threshold during training. | Sprint 1 | ML Engineer | Model Issue | Tuned hyperparameters and improved feature selection. | 2025-10-11 | Closed | Accuracy improved to 90%
8 | QA Engineer | 15/11/2025 | Backend response time slow (>3 sec) for prediction. | Sprint 4 | Backend Developer | Performance | Optimized model loading using lazy initialization. | 15-11-2025 | Closed | Performance is good overall